## Sheet1
Group members:
Dana Crosslin
Sasikumar Chellappan
Software system:
JEdit
Modified classes:
jedit/jEdit/org/gjt/sp/jedit/buffer/JEditBuffer.java
jedit/jEdit/org/gjt/sp/jedit/textarea/TextArea.java
actions.xml
jedit_gui.props
Time spent on this change request:
Initiation | 150 minutes
Concept location | 30 minutes
Impact analysis | 35 minutes
Actualization | 25 minutes
Testing | 40 minutes
20 minutes
Process followed to implement the Change Request:
Initiation
1. Read the assignment documentation provided by Dr.Marcus
2. Read the tool API http://jedit.org/api/index.html to understand specific APIs
3. Download jEdit from https://utdallas.box.com/s/vtiy17c9uh5bbioeghzxevhnvje39knc
4. Unzipped the file jedit.tar.bz2
3. Analyzed the file structure of the project to better understand the flow.
4. Imported aTunes into Eclipse as a Java Project
5. Followed "Tips for Eclipse" under Read README.SRC.txt to resolve the compilation issues with jEdit
6. org/gjt/sp/jedit/jEdit is the main class.
Concept location
Locating to add "unscroll" from the Edit menu
1. Search using String "Undo"
2. jedit_gui.props hold the menu items to be displayed. for ex: below one shows undo is part of edit menu #{{{ Edit menu edit=undo \ redo \
3. actions.xml hold which action to be invoked when particular menu item is clicked for ex: Below one shows when undo is clicked is going to invoke JEditBuffer.undo(textAread) method <ACTION NAME="undo"> <CODE> buffer.undo(textArea); </CODE> </ACTION>
Locating what need to be done when "unscroll" is clicked
1. Put a remote debugger break point in JEditBuffer.undo ( Line # 1942 )
2. Start the jEdit application in Debug mode and opened a File
3. Debugger will stop in Line # 1942 and walked through the code
4. Part of the debugging process we found TextArea.java hold the horizontal and vertical API attributes and currently they marked as Private.
Based on our concept location study, we understood this framework is very similar to any MVC framework out in the market ie: JSF. In which the gui layouts are describe in jedit_gui.props and all the user actions are defined in actions.xml. We decided do the menu changes in jedit_gui.props and user actions in actions.xml and add a new method in JEditBuffer and update the text area properties in TextArea class
Impact analysis
1. Marked the JEditBuffer class as impacted, every user actions are defined in this class.
2. Marekd the TextArea class as impacted, that particular object holds all the text area charactertics.
3. Marked the TextAreaPainter as not impacted, because the change is not going to repaint the text area.
4. Marked the shortcuts.xml as not impacted, we decided not to provide short cut for this unscroll option.
5. Marked textarea.actions.xml also as not impacted, we decided the provide the unscroll option only from Edit menu.
Actualization
Adding unscroll into Edit menu
1. Added unscroll option into jedit_gui.properties, #{{{ Edit menu edit=undo \ redo \ unscroll \
2. Define the action in actions.xml <ACTION NAME="undo"> <CODE> buffer.unscroll(textArea); </CODE> </ACTION>
Implementing action in java code
1. Add unscroll method into JEditBuffer
2. Add two new methods getVerticalJScrollBar and getHorizontalJScrollBar.
3. Make vertical and horizontal variable into public.
Testing
Testcase specific to use case:
1. Start the jEdit from Eclipse
2. Open little large file using File --> Open
3. Notice, horizontal and vertical scroll bars are shown.
4. Click Edit menu, which shows unscroll ( which wasnt there before the change )
5. Click Edit --> unscoll, you will notice the horizonal and vertical sroll bars goes away.
Regression Test cases:
1. Start the JEdit from Eclipse
2. Click File --> Recent Files , which still shows the history of files.
3. Click File --> Recent Files, search a string anywhere from the file and it highlight the file
4. Click File --> Open any file
5. Play with undo and redo , by editing the text file. Make sure the change didn break any of the existing features.
Additional information